## Slide 1
Governance
Sprints and User Engagement
Dependencies
MVP Build
UAT
Aug
Aug
Sep
Oct
Nov
Dec
Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
Sep
S14
S15
S16
S17
S18
S19
S20
S21
S22
S23
S24
S25
S26
S27
S28
S29
S30
S31
S32
S33
S34
S35
S36
S37
S38
Service Management proposal submitted.
Sign-off from funders
IBM Live feed available
BVD Live feed available
UG S&T
UG S&T
UG S&T
UG S&T
UG S&T
UG S&T
UG S&T
UG S&T
UG S&T
Proposal Review and Sign Off
Svce Man Proposal Review and Sign Off
Proposal Signed Off
POG
POG
POG
POG
POG
T&F
T&F
T&F
T&F
T&F
T&F
T&F
T&F
T&F
Project Management and Governance
Develop high level solution design
Develop backlog to deliver solution
Manage backlog and plan sprints
Team stood down awaiting sign-off
Early data modelling (before live data available - over Xmas)
IBM activity to make Sam data feed available
Build infrastructure to support IBM data feed
Build infrastructure to support BVD Free data feed
Load data into SQL models
Begin Power BI reports following early modelling
Complete Power BI reports once live data available
Deploy to Test and QA environments
Deploy to Pre-Prod (for UAT)
Deploy to Prod (following UAT)
Develop RESTful API for users (and to drive UI)
Develop UI
UAT Planning
UAT Preparation
UAT Environment Preparation
UAT1
UAT2
UAT-Complete
Go Live