## UK-View Plan
Task Name | Duration | Start | Finish | Predecessors | Assigned To | % Complete | Visual Flag | Visual Swimlane | Visual Track # Within Swimlane | Visual # Tracks To Cover | Status | Comments
Governance
Customer Group
Technical Working Group
Release Management
Project Management
Planning
Delivery | 75d | 2021-03-31 | 2021-07-13
Sprint Schedule
Sprint 5 | 15d | 2021-03-31 | 2021-04-20 |  |  |  | TRUE | Data Team | 1 | 1
Sprint 9
Release Schedule
R0.01 | 30d | 2021-04-21 | 2021-06-01 |  |  |  | TRUE | Data Team | 2 | 1
Sprint 6 | 10d | 2021-04-21 | 2021-05-04 | 10
Sprint 7 | 10d | 2021-05-05 | 2021-05-18 | 19
Sprint 8 | 10d | 2021-05-19 | 2021-06-01 | 20
R0.01 End | 0
R0.02 | 30d | 2021-06-02 | 2021-07-13 |  |  |  | TRUE | Data Team | 2 | 1
Sprint 9 | 10d | 2021-06-02 | 2021-06-15 | 21
Sprint 10 | 10d | 2021-06-16 | 2021-06-29 | 24
Sprint 11 | 10d | 2021-06-30 | 2021-07-13 | 25
R0.02 End | 0
Release 0.01
Preparation for Release 0.01
Select and agree user stories in scope
Agree dataset used to test capability
Create capability user stories for DevOps
Create data user stories for DevOps
R0.01 Execute sprints
Data Sharing
ScotEID Data Sharing
ScotEID initial data extract
Discuss and agree scope of initial data extract
Agree timing of initial data extract
Receive initial data extract
Absorb initial data extract into environment
ScotEID further data extracts
ScotEID Data Integration
(TBD)
EIDCymru Data Sharing
EIDCymru initial data extract
EIDCymru further data extracts
EIDCymru Data Integration